## FARM POND WM
Farm Ponds GB
Sr. No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC No. | Contact No. | Address | GPS Coordinate |  | Command Area (Kanal) | Design & Cost Estimate Approved Yes/No | Date of Issuance of Work Order | Capacity of Pond (CM) | Size of Pond L,W &D (M) | ICR I Amount Paid to Benificiary (Rs.) 1st Installment @40% CE | ICR I Verified /Deferred | ICR II Amount Paid to Benificiary (Rs.) 2nd Installment @ 40%CE | ICR II Verified /Deferred | Work Order For HEIS Issued Yes/NO | FCR Amount Paid To Benificiary (Rs.) 3rd Installment @ 10% CE | Total Amount Paid to Benificiary (Rs.) | Balance Amount If Any (Rs.) | Status | Remarks
[10 empty] | N | E
1 | 2022-23 | Astore | Bonji | Shaary Bari | Bonji | Muhammad Sabir Khan | - | 3555600696 | Bunji Astore | N35.632216° | E74.615987° | 7 | yes | 30/8/2022 | 292.42 | 10.67,10.67,2.44 | 316178.88 | Verified | 0 | 0 | No | 212257 | 528728.3 | 0 | Incomplete | Deferred
2 | 2022-23 | Astore | Bonji | Bunji Astore | Bonji | Israr Ahmad | 7120178805897 | 3555600692 | Bunji Astore | N35.663901° | N74.627001° | 8 | yes | 30/8/2023 | 292.42 | 10.67,10.67,2.45 | 320018 | Verified | 0 | 0 | No | 384424.94 | 704442.94 | 0 | Completed | Reverified
3 | 2022-23 | Hunza | Hunza | Moorkhun | Moorkhun | Ali Muhammad | 7150504107813 | 3555261601 | Moorkhun Hunza | N36.609132° | E74.861567° | 8 | yes | 30/8/2022 | 276.13 | 10.66,10.66,2.44 | 216128 | Verified | 0 | 0 | No | 310086 | 526490.13 | 0 | Completed | Reverified
4 | 2022-23 | Hunza | Hunza | Nasirabad | Nasirabad | Gulbaz | 7150403908749 | 3444298917 | Nasirabad | N36.254033 | E74.550350 | 5 | yes | 30/8/2023 | 193.41 | 11.28,11.28,1.52 | 207968 | Verified | 0 | 0 | No | 531725 | 739693 | 0 | Completed | Reverified
5 | 2022-23 | Ghanche | Abadan | Abadan | Chorbat | Shamsher Ali | 7130245353073 | 3554135077 | Abadan Masahabrum | N35.894327 | E74.437837 | 20 | yes | 2022-06-12 | 162.06 | 10.36,7.31,2.13 | 190248 | Verified | 285373 | 0 | No | 0 | 475622 | 0 | Completed | Reverified
6 | 2022-23 | Ghanche | Chorbat | Shorbat | Chorbat | Muhammad | 7130174102199 | 3555274629 | Siyari Shorbat | N35.190340 | E73.717302 | 15 | yes | 2022-06-12 | 162.06 | 10.36,7.31,2.14 | 190248 | Verified | 285373 | 0 | No | 0 | 475621 | 0 | Completed | Reverified
7 | 2022-23 | Skardu | Gamba | Gamba | Gamba | Ghulam haider | 7110380629947 | 3469555197 | Dr niyzi plot Gamba skd | N35.190340 | E75.315566 | 5 | yes | 2022-09-06 | 381.2 | 13.41,1036,2.74 | 238949 | Verified | 0 | 0 | No | 198240 | 437189 | 0 | Completed | Reverified
8 | 2022-23 | Skardu | Hussain Abad | Hussain Abad | Hussainabad | Mohd raza | 7110333112175 | 3129902715 | Bain hussain abad skd | N35.311480 | E75.692225 | 8 | yes | 2022-09-06 | 169.9 | 9.14,7.62,2.44 | 238163 | Verified | 0 | 0 | No | 356044 | 594207 | 0 | Completed | Reverified
9 | 2022-23 | Shigar | Shigar | Gulapur | Gulapur | Imtiaz sagar | 7220103393855 | 3554510596 | Gulapur shigar | N35.574091 | E75.547681 | 5 | yes | 2022-09-06 | 380 | 14.0,10.97,2.47 | 270850 | Verified | 0 | 0 | No | 405076 | 675926 | 0 | Completed | Reverified
10 | 2022-23 | Ghizar | kanchay | Kanchay | Kachy | Wajahat hussain | 7140272634443 | 3555109317 | Kanchy ghizar | N36.183126 | E73.789542 | 8 | yes | 30/8/2022 | 36 | 4.26,3.96,2.13 | 243605.44 | Verified | 0 | 0 | No | 36715.31 | 280320.75 | 0 | Completed | Reverified
11 | 2022-23 | Gilgit | Danyore | Muhammad Abad | Danyore | Anjum Ali | 7120102183967 | 3555023335 | Muhammad Abad Danyore | N35.894327 | E74.387114 | 10 | yes | 30/8/2023 | 176 | 10.06,6.4,2.74 | 247819 | Verified | 0 | 0 | No | 118412 | 457789 | 0 | Completed | Reverified
12 | 2022-23 | Gilgit | Danyore | Kashero Het | Danyore | Yasir Abbas | 4250115674395 | 3469235510 | Kashero Het Danyore | N35.907676 | E74.387114 | 5 | yes | 30/8/2024 | 213 | 9.14,8.53,2.74 | 256875.84 | Verified | 0 | 0 | No | 200731.88 | 572008.6 | 0 | Completed | Reverified
13 | 2022-23 | Gilgit | Danyore | Chamogarh | Chamogarh | Ahtisham | 7150106974973 | 3468003668 | Chamogarh | N35.858231° | E74.522933° | 7 | yes | 2022-09-07 | 293.7 | 10.97,10.97,2.44 | 0 | Verified | 0 | 0 | No | 648580.01 | 648580.01 | 0 | Completed | Reverified
14 | 2022-23 | Nagar | Nagar | Madarsa (Nilt jaffarabad) | Jaffarabad | Altaf Hussain | 7150396923973 | 3555600692 | Nilt Jaffarabad | N36.140551 | E73.789542 | 8 | yes | 2022-09-06 | 211 | 8.23,7.01,3.65 | 214469.12 | Verified | 0 | 0 | No | 224333.9 | 438803.02 | 0 | Completed | Reverified
15 | 2022-23 | Nagar | Nagar | Chalt pain | Chalt | Syed Altaf | 7150303134435 | 3555133329 | Chalt Pain | N36.206663° | E74.310963° | 8 | yes | 2022-09-06 | 217.6 | 12.19,7.31,2.44 | 207968 | Verified | 0 | 0 | No | 297809.2 | 505777.2 | 0 | Completed | Reverified
16 | 2022-23 | Diamer | Thorli Das | Thorli Das | Chilas | Muhammad Zikriya | 7120247866039 | 3555032592 | Thurli Das | N35.486145° | E73.897267° | 8 | yes | 2022-09-06 | 338 | 13.41,10.36,2.44 | 337445.44 | Verified | 200000 | 0 | No | 0 | 479791.8 | 0 | Completed | Reverified
17 | 2022-23 | Ghizer | Gahkuch | Das Japuky | Gahkuch | Sher Khan | - | 3554528162 | Das japuky | - | - | 7 | Yes | 2022-09-06 | 380 | 14.0,10.97,2.47 | 270850.8 | - | 0 |  | No |  | 223630.4 | 0 | Completed | Reverified
18 | 2022-23 | Shigar | Shigar | Quak thang | Quakthang | Raja Adeel Anjum | 71102-3040881-5 | 3442211744 | Quackthang Shigar | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Offered | Pending
19 | 2022-23 | Ghizer | Yasin | Noh Yasin | Noh Yasin | Akbar khab | 71401-5919115-1 | 3555277590 | Noh Yasin Ghizer | - | - | 8 | Yes | 30/8/2022 | - | 9.14,8.84,1.23 | 258837.44 | - | - | 0 | No | - | 195845.64 | - | Completed | Reverified
20 | 2022-23 | Kharmang | Kharmang | Mehdi Abad | Mehdi Abad | M Abbas | 42401-6001802-1 | 3555273379 | Mehdi Abad | - | - | 7 | Yes | 30/8/2022 | - | 11.5,8.8,2.7 | 230743 | - | - | - | - | 325357 | 556100.48 | - | Completed | Reverified

## Solar on Farm Pond
Solar Pumping System On Farm Pond Cost Sharing 60:40
Solar Pumping System On Farm Pond
Sr. No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC | Contact No. | Address | GPS Coordinate |  | Intervention Farm Pond/Dug Well | Command Area | Capacity (KW) | Cost Estimate Rs. | Govt Share as Per PC-I Rs. | Govt Share@ 80% of CE (Rs.) | Design & Cost Estimate Approval Date | Issuance of Work Order Date | Farmer Share As per PC-I Rs. | Farmers Share@ 20% of CE (Rs.) | Diffrence Rs. | 1st Installment @ 40% of CE (Rs.) | 2nd Installment @ 40% of CE (Rs.) | Total Amount Paid to SSC (Rs.) | Total Expenditure Incurred (Rs.) | Retention Money @ 10% 0f Total Expenditure (RS.) | Status | Remarks
[10 empty] | N | E
1 | 2022-23 | Astore | Bonji | Shaary Bari | Bonji | Muhammad Sabir Khan | - | 3555600696 | Bunji Astore | N35.632216° | E74.615987° | Farm Pond | 7 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 0 | 0 | 0 | 0 | Incomplete | Deferred
2 | 2022-23 | Astore | Bonji | Bunji Astore | Bonji | Israr Ahmad | 7120178805897 | 3555600692 | Bunji Astore | N35.663901° | N74.627001° | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
3 | 2022-23 | Hunza | Hunza | Moorkhun | Moorkhun | Ali Muhammad | 7150504107813 | 3555261601 | Moorkhun Hunza | N36.609132° | E74.861567° | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 742992 | 1059600 | 1059600 | 0 | Completed | Reverified
4 | 2022-23 | Hunza | Hunza | Nasirabad | Nasirabad | Gulbaz | 7150403908749 | 3444298917 | Nasirabad | N36.254033 | E74.550350 | Farm Pond | 5 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
5 | 2022-23 | Ghanche | Abadan | Abadan | Mashaburum | Shamsher Ali | 7130245353073 | 3554135077 | Abadan Masahabrum | N35.894327 | E74.437837 | Farm Pond | 20 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1059600 | 1059600 | 0 | Completed | Reverified
6 | 2022-23 | Ghanche | Chorbat | Shorbat | Chorbat | Muhammad | 7130174102199 | 3555274629 | Siyari Shorbat | N35.190340 | E73.717302 | Farm Pond | 15 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 531072 | 1059600 | 1059600 | 0 | Completed | Reverified
7 | 2022-23 | Skardu | Gamba | Gamba | Gamba | Ghulam haider | 7110380629947 | 3469555197 | Dr niyzi plot Gamba skd | N35.190340 | E75.315566 | Farm Pond | 5 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 531072 | 1059600 | 1059600 | 0 | Completed | Reverified
8 | 2022-23 | Skardu | Hussain Abad | Hussain Abad | Hussainabad | Mohd raza | 7110333112175 | 3129902715 | Bain hussain abad skd | N35.311480 | E75.692225 | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 531072 | 1059600 | 1059600 | 0 | Completed | Reverified
9 | 2022-23 | Shigar | Shigar | Gulapur | Gulapur | Imtiaz sagar | 7220103393855 | 3554510596 | Gulapur shigar | N35.574091 | E75.547681 | Farm Pond | 5 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 531072 | 1059600 | 1059600 | 0 | Completed | Reverified
10 | 2022-23 | Ghizar | kanchay | Kanchay | Kachy | Wajahat hussain | 7140272634443 | 3555109317 | Kanchy ghizar | N36.183126 | E73.789542 | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 620712 | 1068600 | 1068600 | 0 | Completed | Reverified
11 | 2022-23 | Gilgit | Danyore | Muhammad Abad | Danyore | Anjum Ali | 7120102183967 | 3555023335 | Muhammad Abad Danyore | N35.894327 | E74.387114 | Farm Pond | 10 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
12 | 2022-23 | Gilgit | Danyore | Kashero Het | Danyore | Yasir Abbas | 4250115674395 | 3469235510 | Kashero Het Danyore | N35.907676 | E74.387114 | Farm Pond | 5 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
13 | 2022-23 | Gilgit | Danyore | Chamgarh | Chamogarh | Ahtisham | 7150106974973 | 3468003668 | Chamogarh | N35.858231° | E74.522933° | Farm Pond | 7 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
14 | 2022-23 | Nagar | Nagar | Madarsa (Nilt jaffarabad) | Jaffarabad | Altaf Hussain | 7150396923973 | 3555600692 | Nilt Jaffarabad | N36.140551 | E73.789542 | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
15 | 2022-23 | Nagar | Nagar | Chalt pain | Chalt | Syed Altaf | 7150303134435 | 3555133329 | Chalt Pain | N36.206663° | E74.310963° | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 538272 | 1068600 | 1068600 | 0 | Completed | Reverified
16 | 2022-23 | Diamer | Thori Das | Thurli Das | Chilas | Muhammad Zikriya | 7120247866039 | 3555032592 | Thurli Das | N35.486145° | E73.897267° | Farm Pond | 8 | 5.5 | 989400 | 800000 | 791520 | 2022-05-31 | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 672972 | 1059600 | 1059600 | 0 | completed | Reverified
17 | 2022-23 | Ghizer | Gahkuch | Das Jpuky | Gahkuch | Sher khan | - | 3554528162 | Das japuky | - | - | Farm pond | 7 | 5.5 | 989400 | 800000 | 791520 | - | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 620712 | 1059000 | 1059000 | - | Completed | Reverified
18 | 2022-23 | Shigar | Shigar | Quakthang | Quacthang | Raja Adeel Anjum | 71102-3040881-5 | 3442211744 | Quakthang | - | - | Farm pond | 7 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | Offered | Pending
19 | 2022-23 | Ghizer | Yasin | Noh Yasin | Noh Yasin | Akbar khan | 71401-5919115-1 | 3555277590 | Noh yasin | - | - | Farm pond | 7 | 5.5 | 989400 | 800000 | 791520 | - | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 620712 | 1059600 | 1059600 | - | Completed | Reverified
20 | 2022-23 | Kharmang | Kharmang | Mehdi Abad | Mehdi Abad | M Abbas | 42401-6001802-1 | 3555273379 | Mehdi Abad | - | - | Farm pond | 7 | 5.5 | 989400 | 800000 | 791520 | - | 2022-05-31 | 200000 | 197880 | 2120 | 316608 | 742992 | 1059600 | 1059600 | - | Completed | Reverified

## Fruit Plants and Fodder
Fruit Plants and Fodder GB
Sr.No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC No. | Contact No. | Address | GPS Coordinate |  | Land Holding | Water Source | Covered Area (Acers) |  |  | Amount Paid to Benificiary (Rs.) | Final Bill to Pay | Status | Remarks
[14 empty] | Fruit Orchard | Oil seeds/ Pulses | Fodder
1 | 2022-23 | Astore | Bonji | Shaary Bari | Bonji | Muhammad Sabir Khan | - | 3555600696 | Bunji Astore | N35.632216° | E74.615987° | 7 | River | 0 | 0 | 0 | 0 | 0 | Incomplete | Deffered
2 | 2022-23 | Astore | Bonji | Bunji Astore | Bonji | Israr Ahmad | 7120178805897 | 3555600692 | Bunji Astore | N35.663901° | N74.627001° | 8 | River | 5 |  | 6 | 121333 | 98167 | Completed | R-Verified
3 | 2022-23 | Hunza | Hunza | Moorkhun | Moorkhun | Ali Muhammad | 7150504107813 | 3555261601 | Moorkhun Hunza | N36.609132° | E74.861567° | 8 | River | 4 | 0 | 4 | 121333 | 40667 | Completed | R-Verified
4 | 2022-23 | Hunza | Hunza | Nasirabad | Nasirabad | Gulbaz | 7150403908749 | 3444298917 | Nasirabad | N36.254033 | E74.550350 | 8 | River | 2 | 0 | 2.6 | 104800 | 23100 | Completed | Verified
5 | 2022-23 | Ghanche | Abadan | Abadan | Chorbat | Shamsher Ali | 7130245353073 | 3554135077 | Abadan Masahabrum | N35.894327 | E74.437837 | 20 | River | 7 | 0 | 2.761 | 121333 | 90100 | Completed | R-Verified
6 | 2022-23 | Ghanche | Chorbat | Shorbat | Chorbat | Muhammad | 7130174102199 | 3555274629 | Siyari Shorbat | N35.190340 | E73.717302 | 15.25 | River | 7 | 0 | 2.761 | 121333 | 90100 | Completed | R-Verified
7 | 2022-23 | Skardu | Gamba | Gamba | Gamba | Ghulam haider | 7110380629947 | 3469555197 | Dr niyzi plot Gamba skd | N35.190340 | E75.315566 | 5 | River | 5 | 0 | 2.76 | 121333 | 43100 | Completed | R-Verified
8 | 2022-23 | Skardu | Hussain Abad | Hussain Abad | Hussainabad | Mohd raza | 7110333112175 | 3129902715 | Bain hussain abad skd | N35.311480 | E75.692225 | 8.75 | River | 5 | 0 | 2.76 | 121333 | 43100 | Completed | R-Verified
9 | 2022-23 | Shigar | Shigar | Gulapur | Gulapur | Imtiaz sagar | 7220103393855 | 3554510596 | Gulapur shigar | N35.574091 | E75.547681 | 8 | River | 1 | 0 | 1 | 114213 | 0 | Completed | R-Verified
10 | 2022-23 | Ghizar | kanchay | Kanchay | Kachy | Wajahat hussain | 7140272634443 | 3555109317 | Kanchy ghizar | N36.183126 | E73.789542 | 18.87 | River | 7 | 0 | 7 | 114773 | 209227 | Completed | R-Verified
11 | 2022-23 | Gilgit | Danyore | Muhammad Abad | Danyore | Anjum Ali | 7120102183967 | 3555023335 | Muhammad Abad Danyore | N35.894327 | E74.387114 | 8 | River | 3 | 0 | 2 | 112000 | 0 | Completed | Reverified
12 | 2022-23 | Gilgit | Danyore | Kashero Het | Danyore | Yasir Abbas | 4250115674395 | 3469235510 | Kashero Het Danyore | N35.907676 | E74.387114 | 8 | River | 2.5 | 0 | 3.5 | 94960 | 23290 | Completed | Reverified
13 | 2022-23 | Gilgit | Danyore | Chamgarh | Chamogarh | Ahtisham | 7150106974973 | 3468003668 | Chamogarh | N35.858231° | E74.522933° | 7 | River | 5 | 0 | 5 | 0 | 202500 | Completed | R-Verified
14 | 2022-23 | Nagar | Nagar | Madarsa (Nilt jaffarabad) | Jaffarabad | Altaf Hussain | 7150396923973 | 3555600692 | Nilt Jaffarabad | N36.206663° | E74.310963° | 8 | River | 6.5 | 0 | 6 | 105653 | 149097 | Completed | R-Verified
15 | 2022-23 | Nagar | Nagar | Chalt pain | Chalt | Syed Altaf | 7150303134435 | 3555133329 | Chalt Pain | N36.206663° | E74.310963° | 8 | River | 5 | 0 | 6 | 106720 | 112780 | Completed | R-Verified
16 | 2022-23 | Diamer | Thori Das | Thurli Das | Chilas | Muhammad Zikriya | 7120247866039 | 3555032592 | Thurli Das | N35.486145° | E73.897267° | 8 | River | 6 | 0 | 5 | 152400 | 123600 | Completed | R-Verified
17 | 2022-23 | Ghizer | Punial | Das japuky | Das japuky | Sher khan | - | 3554528162 | Das japuky | - | - | 7 | River | 4 | 0 | 6 | 107440 | 88560 | Completed | R-verified
18 | 2022-23 | Shigar | Shigar | Quakthang | Quakthang | Raja Adeel Anjum | 71102-3040881-5 | 3442211744 | Quakghang | - | - | 8 | Bore | - | - | - | - | - | Offered | Pending
19 | 2022-23 | Ghizer | Yasin | Noh yasin | Noh yasin | Akbar khan | 71401-5919115-1 | 3555277590 | Noh yasin | - | - | 7 | River | 5 | 0 | 6 | 107440.03 | 112059. 97 | Completed | R-verified
20 | 2022-23 | Kharmang | Kharmang | Mehdi Abad | Mehdi Abad | M Abbas | 42401-6001802-1 | 3555273379 | Mehdi Abad | - | - | 7 | River | 5 | 0 | 6 | 103120 | 116380 | Completed | R-verified