## Farm Pond
Farm Pond
Sr. No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC No. | Contact No. | Address | GPS Coordinates N E |  | Command Area | Area to be Irrigated | Estimated Cost (Rs.) | Date of Issuance Of TS | Capacity of Pond C.ft | Size of Pond L,W & D (ft) | Date of Approval for Execution of Scheme | Date of Completion of Scheme | Total Expenditure Incurred (Rs.) | Date of Payment to Farmer / Firm (Rs.) | Amount Paid to Farmer / Firm (Rs.) | Status | Remarks | Observations
1 | 2020-21 | Islamabad | Islamabad | Mughal | Mughal | Azhar Hussain Mirza | 61101-9106131-3 | 0344-7443444 | Mughal | 33.557 | 73.237 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 15000 | 50'X60'X5' | 2021-03-09 | 2021-03-31 | 960,000/- | 2021-05-27 | 960,000/- | Completed | Reverified
2 | 2020-21 | Islamabad | Islamabad | Mughal | Mughal | Mudassar Iqbal Mirza | 61101-6372843-9 | 0314-5373290 | Mughal | 33.5448 | 73.2482 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 19500 | 50X60X6.5 | 2021-03-11 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified
3 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Rehmat Ullah | 61101-6131803-7 | 0345-5409449 | Tumair | 33.6768 | 73.2627 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 21000 | 50'X60'X7' | 2021-03-09 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
4 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Anwar Kamal | 61101-5576947-5 | 0333-5184411 | Tumair | 33.6751 | 73.2882 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 21000 | 50'X60'X7' | 2021-03-09 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
5 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Zafran | 61101-6335155-5 | 0333-1562699 | Tumair | 33.6901 | 73.2806 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 15600 | 80'X30'X6.5' | 2021-03-09 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
6 | 2020-21 | Islamabad | Islamabad | Phulgrahan | Phulgrahan | Raja Majid Aftab | 61101-5372044-1 | 0300-5404044 | Phulgrahan | 33.7586 | 73.243 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 37440 | 65'X64'X9' | 2021-03-09 | 2021-03-30 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
7 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Zafar Iqbal Ghondal | 61101-2037350-1 | 0345-8543158 | Tumair | 33.7199 | 73.2736 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 21000 | 50'X60'X7' | 2021-03-09 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
8 | 2020-21 | Islamabad | Islamabad | Begwal | Begwal | Rasool Rais | 61101-1861879-9 | 0333-5331444 | Begwal | 33.7167 | 73.2752 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-03-01 | 20233 | 71.75'X47'X6' | 2021-03-09 | 2021-03-29 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
9 | 2021-2022 | Islamabad | Islamabad | Begwal | Begwal | Fatima Mufassar | 61101-1861941-0 | 0300-8550408 | Begwal | 33.7217 | 73.2726 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 60122 | 36.66'X160'X10.25' | 2021-11-24 | 2022-01-14 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Deffered | • Leakage below the outlet.
10 | 2021-2022 | Islamabad | Islamabad | Jhandala | Sihala | Raja Safdar Khan | 61101-2249852-36 | 0345-5111912 | Jhandala | 33.7223 | 73.2698 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 15600 | 80'X30'X6.5' | 2021-11-24 | 2022-01-25 | 960,000/- | 2021-05-21 | 960,000/- | Completed | Reverified | -
11 | 2021-22 | Islamabad | Islamabad | Kijnah | Kijnah | Zahid Mehmood | 61101-2020831-7 | 0345-8570607 | Kijnah | 33.685 | 73.34 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 20233 | 71.75X47X6 | 2021-11-24 | 2022-01-14 | 960,000/- | 2022-05-20 | 960,000/- | Completed | Reverified
12 | 2021-22 | Islamabad | Islamabad | Mughal | Tumair | Muhammad Jamraiz | 61101-4546999-1 | 0342-9018818 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 20 Kanal | 1,200,000/- | 2021-11-08 | 19500 | 50X60X6.5 | 2021-11-24 | 2022-01-25 | 960,000/- | 2022-05-19 | 960,000/- | Completed | Reverified
13 | 2022-23 | Islamabad | Islamabad | Arah | Saidpur | Mian Abdul Rauf | 61101-7461690-5 | 0300-5006145 | Arah | 33.6346 | 73.2387 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 15600 | 80'X30'X6.5' | 2022-11-21 | 2023-03-27 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
14 | 2022-23 | Islamabad | Islamabad | Pija | Pagh Panwal | Zarat Hussain | 61101-2016744-3 | 0344-0742252 | Pija | 33.5993 | 73.2379 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 41064 | 58'X60'X11.8' | 2022-11-21 | 2023-03-27 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
15 | 2022-23 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Sohail Qurashi | 61101-1987197-5 | 0300-8560929 | Tumair | 33.6741 | 73.2806 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 19500 | 50'X60'X6.5' | 2022-11-21 | 2023-03-28 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Deffered | • Outlet is Damage, need earthern work.
16 | 2022-23 | Islamabad | Islamabad | Mughal | Mughal | Raja Awais Arshad | 61101-7115860-3 | 0310-5659713 | Mughal | 33.5448 | 73.2482 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 19500 | 50X60X6.5 | 2022-11-21 | 2023-03-27 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified
17 | 2022-23 | Islamabad | Islamabad | Tumair | Tumair | Waqas Muhammad Raja | 61101-144622-7 | 0332-5131626 | Tumair | 33.6712 | 73.2857 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 37440 | 65'X64'X9' | 2022-11-21 | 2023-03-28 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
18 | 2022-23 | Islamabad | Islamabad | Sihala | Sihala | Muhammad Umair zafar | 61101-1911995-9 | 0300-4036406 | Sihala | 33.5527 | 73.2565 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 37440 | 65'X64'X9' | 2022-11-21 | 2023-03-29 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
19 | 2022-23 | Islamabad | Islamabad | Tumair | Tumair | Ikram ul Haq | 61101-9711337-1 | 0340-5346393 | Tumair | 33.6658 | 73.2892 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 15600 | 80'X30'X6.5' | 2022-11-21 | 2023-03-29 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
20 | 2022-23 | Islamabad | Islamabad | Sihala | Sihala | Moeen Akhtar | 37405-6734866-5 | 0314-5373290 | Sihala | 33.5544 | 73.2541 | 20 Kanal | 20 Kanal | 1,200,000/- | 2022-11-14 | 19500 | 50'X60'X6.5' | 2022-11-21 | 2023-03-30 | 960,000/- | 2023-06-23 | 960,000/- | Completed | Reverified | -
21 | 2024-2025 | Islamabad | Islamabad | Mohra |  | Muhammad Dawood | 33102-1542688-7 | 0344-0742252 | Mohra Tehsil & Dist.Islamabad | 33.6899 | 73.2807 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
22 | 2024-2025 | Islamabad | Islamabad | Tumair |  | Muhammad Muddasir | 32201-9268304-9 | 0300-4036406 | Tumair Tehsil & Dist.Islamabad | 33.6766 | 73.2879 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
23 | 2024-2025 | Islamabad | Islamabad | Pind Bhegwal |  | Ikram Rasool | 61101-1976372-5 | 0300-9643890 | Pind Bhegwal Tehsil & Dist.Islamabad | 33.7224 | 73.2707 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
24 | 2024-2025 | Islamabad | Islamabad | Phinot |  | Rukhsana Kausar | 37101-731988-8 | 0305-7984660 | Phinot Tehsil & Dist.Islamabad | 33.6795 | 73.2973 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
25 | 2024-2025 | Islamabad | Islamabad | Moriyan |  | Akhtar Hussain | 33303-2185483-1 | 0346-7235232 | Moriyan Tehsil & Dist.Islamabad | 33.6741 | 73.2806 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
26 | 2024-2025 | Islamabad | Islamabad | Tumair |  | Muhammad Sharaz | 37405-230999-9 | 0333-8229266 | Tumair Tehsil & Dist.Islamabad | 33.6866 | 73.2945 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
27 | 2024-2025 | Islamabad | Islamabad | Tumair |  | Samar Sajid | 31304-448803-8 | 0300-7653377 | Tumair Tehsil & Dist.Islamabad | 33.6853 | 73.3324 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
28 | 2024-2025 | Islamabad | Islamabad | Moriyan |  | Waqas Muhammad Raja | 611016-144622-7 | 0332-5131626 | Moriyan Tehsil & Dist.Islamabad | 33.6798 | 73.2711 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
29 | 2024-2025 | Islamabad | Islamabad | Kijna |  | Faisal Iqbal | 61104-1873191-3 | 0335-8354301 | Kijna Tehsil & Dist.Islamabad | 33.687 | 73.295 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
30 | 2024-2025 | Islamabad | Islamabad | Pind Bhegwal |  | Raja Mujahid | 61101-4803364-3 | 0304-2081112 | Pind Bhegwal Tehsil & Dist.Islamabad | 33.7224 | 73.2707 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
31 | 2024-2025 | Islamabad | Islamabad | Phulgrahan |  | Saif Ullah | 34301-8482222-7 | 0303-2809771 | Tehsil & Dist.Islamabad | 33.7597 | 73.2428 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
32 | 2024-2025 | Islamabad | Islamabad | Tumair |  | Rahmat Ullah | 61101-6131803-7 | 0312-5409449 | Tumair Tehsil & Dist.Islamabad | 33.6754 | 73.269 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved
33 | 2024-2025 | Islamabad | Islamabad | Thanda Pani |  | Muneeb ur Rehman | 61101-3317120-9 | 0314-5373290 | Thanda Pani Tehsil & Dist.Islamabad | 33.6871 | 73.2954 | 20 Kanal | 20 Kanal | 1,200,000/- |  | 201987 | 50x60x9 | N/A |  |  |  |  | Design Vetting | Approved

## Solar Farm POND
Solar Pumping System On Farm Pond
Sr. No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC | Contact No. | Address | GPS Coordinates N E |  | Command Area | Capacity (Hp) | Cost Estimate (Rs.) | Issuance of TS Date | Approval for Execution of Scheme Date | Expenditures Incurred(Rs.) | Amount Paid To Farmer / Firm (Rs.) | Status | Remarks | Observations
1 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Zafran | 61101-6335155-5 | 3331562699 | Tumair | 33.6906 | 73.2812 | 20 Kanal | 5HP | 917573 | 2021-04-14 | 2021-05-18 | 734058 | 734058 | Completed | Deferred | • Inverter was not available at site
2 | 2020-21 | Islamabad | Islamabad | Chirah | Chirah | Raja Shahzad Sultan | 61101-2422638-3 | 0345-5322226 | Chirah | 33.6488 | 73.3121 | 20 Kanal | 5HP | 917573 | 2021-04-14 | 2021-04-26 | 734058 | 734058 | Completed | Reverified | -
3 | 2020-21 | Islamabad | Islamabad | Mera Begwal | Mera Begwal | Mujahid Hussain | 61101-7546213-5 | 0346-5002928 | Mera Begwal,Islamabad | 33.74 | 73.25 | 20 Kanal | 5HP | 917573 | 2021-05-05 | 2021-02-17 | 734058 | 734058 | Completed | Reverified | -
4 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Sher Bahadar Zada Khan | 15601-2069294-5 | 0334-5256927 | Tumair,Islamabad | 33.67 | 73.28 | 20 Kanal | 5HP | 917573 | 2021-05-05 | 2021-02-17 | 734058 | 734058 | Completed | Deffered | 1. System was not available at site
5 | 2020-21 | Islamabad | Islamabad | Pahg | Pahg | Muhammad Arshad Khan Kiyani | 37405-0675547-7 | 0321-5246413 | Pahg,islamabad | 33.44 | 73.08 | 20 Kanal | 5HP | 917573 | 2021-05-05 | 2021-02-17 | 734058 | 734058 | Completed | Reverified | -
6 | 2020-21 | Islamabad | Islamabad | Mughal, Islamabad | Mughal | Azhar Hussain Mirza | 61101-9106131-3 | 3447443444 | Mughal, Islamabad | 33,33',10'' | 73,15',23'' | 20 Kanal | 5HP | 917573 | 2021-04-15 | 2021-04-27 | 734058 | 734058 | Damage | Deferred | • Solar panels were damaged.
7 | 2020-21 | Islamabad | Islamabad | Tumair , Islamabad | Tumair | Numan Hassan | 61101-4786585-1 | 3095637208 | Tumair , Islamabad | 33',40',47'' | 73'16,16'' | 20 Kanal | 5HP | 917573 | 2021-04-16 | 2021-04-28 | 734058 | 734058 | Completed | Reverified | -
8 | 2022-23 | Islamabad | Islamabad | Sihala | Sihala | Muhammad Umair Zafar | 61101-1911995-5 | 3004036406 | Sihala | 33.5523 | 73.2563 | 20 Kanal | 5HP | 917573 | 2022-11-14 | 2023-03-28 | 734058 | 734058 | Completed | Reverified | -
9 | 2022-23 | Islamabad | Islamabad | Sihali | Sihali | Tashfeen Khan | 17301-8957652-9 | 3018581916 | Sihali | 33.7068 | 73.2598 | 20 Kanal | 5HP | 917573 | 2022-11-14 | 2023-03-28 | 734058 | 734058 | Completed | Reverified | -
10 | 2024-2025 | Islamabad | Islamabad | Mohra | - | Muhammad Dawood | 33102-1542688-7 | 3440742252 | Mohra Islamabad | 33.6899 | 73.2807 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
11 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Muhammad Muddasir | 32201-9268304-9 | 3004036406 | Tumair Islamabad | 33.6766 | 73.2879 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
12 | 2024-2025 | Islamabad | Islamabad | Pind Bhegwal | - | Ikram Rasool | 61101-1976372-5 | 3096438900 | Pind Bhegwal Islamabad | 33.7224 | 73.2707 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
13 | 2024-2025 | Islamabad | Islamabad | Moriyan | - | Akhtar Hussain | 33303-2185483-1 | 3467235232 | Moriyan Islamabad | 33.6741 | 73.2806 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
14 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Muhammad Sharaz | 37405-230999-9 | 3338229266 | Tumair Islamabad | 33.6866 | 73.2945 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
15 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Samara Sajid | 31304-448803-8 | 3007653377 | Tumair Islamabad | 33.6853 | 73.3324 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
16 | 2024-2025 | Islamabad | Islamabad | Moriyan | - | Waqas Muhammad Raja | 611016-144622-7 | 3325131626 | Moriyan Islamabad | 33.6798 | 73.2711 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -
17 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Rahmat Ullah | 61101-6131803-7 | 3125409449 | Tumair Islamabad | 33.6754 | 73.269 | 20 Kanal | 5HP | 1000000 | - | - | - | - | Design Vett. | Approved | -

## DW
Dug Wells
Sr. No. | Fiscal YEAR | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC No. | Contact No. | Address | GPS Coordinates N E |  | Command Area | Area to be irrigated | Estimated Cost (Rs.) | Date of Issuance Of TS | Dia Of Dug Well | Depth of Dug Well | Date of Approval for Execution of Scheme | Date of Completion Of Scheme | Total Expenditure Incurred (Rs.) | Date of Payment to Farmer /Firm | Amount Paid to Farmer /Firm(Rs.) | Status | Remarks
1 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Zafar Mehmood | 61101-6626868-9 | 0311-5086500 | Tumair | 33.67507 | 73.29504 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 31-03-21 | 640,000/- | 31-04-21 | 640,000/- | Completed | Reverified
2 | 2020-21 | Islamabad | Islamabad | Phulgraha | Chirah | Raja Ishtiaq | 61101-9998808-9 | 0300-5569632 | Phulgraha | 33.75081 | 73.26142 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 20-04-21 | 640,000/- | 20-05-21 | 640,000/- | Completed | Reverified
3 | 2020-21 | Islamabad | Islamabad | Saidpur | Araha | Zahid Hussain | 61101-0226457-3 | 0345-5005597 | Araha | 33.62994 | 73.24441 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 05-04-21 | 640,000/- | 05-05-21 | 640,000/- | Completed | Reverified
4 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Ijaz | 61101-2814196-9 | 0345-8597702 | Tumair | 33.68806 | 73.29511 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 11-03-21 | 15-04-21 | 640,000/- | 15-06-21 | 640,000/- | Completed | Reverified
5 | 2020-21 | Islamabad | Islamabad | Sarai Madhu | Sarai Madhu | Syed Tanveer Haider | 61101-1916562-9 | 0333-5107211 | Sarai Madhu | 33.671 | 72.866 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 31-03-21 | 640,000/- | 09-06-21 | 640,000/- | Completed | Reverified
6 | 2020-21 | Islamabad | Islamabad | Gohkina | Gohkina | Muhammad Saddique | 61101-6131688-5 | 0333-5289328 | Gohkina | 33.768 | 73.0658 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 31-03-22 | 640,000/- | 09-06-21 | 640,000/- | Completed | Reverified
7 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Azeem Khan | 61101-7554811-7 | 0348-9513755 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 12-03-21 | 20-04-22 | 640,000/- | 09-06-21 | 640,000/- | Completed | Reverified
8 | 2020-21 | Islamabad | Islamabad | Kijna,Islamabad | Tumair | Tahir Mehmood | 61101-2020830-3 | 0345-8570607 | Kijna | 33.68 | 73.15 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-2021 | 12 Ft | 65 Ft | 15-03-2021 | 16-04-2021 | 640,000/- | 14-06-2021 | 640,000/- | Completed | ReVerified
9 | 2020-21 | Islamabad | Islamabad | Moryan | Kurri | Ijaz Ahmed | 61101-1981820-9 | 0316-4895558 | Moryan | 33,41,17 | 73,17,42 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65Ft | 15-03-21 | 31-03-21 | 640,000/- | 27-05-21 | 640,000/- | Complete | Reverified
10 | 2020-21 | Islamabad | Islamabad | Mughal | Mughal | Ulfat Hussain Mirza | 61101-1783618-1 | 03135190331 | Mughal | 33.5448 | 73.2482 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12Ft | 65Ft | 12-03-21 | 31-03-21 | 640,000/- | 14-06-21 | 640,000/- | Completed | Reverified
11 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Younas | 37405-5386315-3 | 03015215408 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 20 Kanal | 800,000/- | 01-03-21 | 12 Ft | 65 Ft | 11-03-21 | 15-04-21 | 640,000/- | 14-06-21 | 640,000/- | Completed | Reverified
12 | 2021-22 | Islamabad | Islamabad | Tumair | Tumair | Raja Niaz Muhammad | 61101-1812070-5 | 0300-5254505 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-21 | 12Ft | 65Ft | 24-11-21 | 25-01-22 | 640,000/- | 20-05-22 | 640,000/- | Completed | Reverified
13 | 2021-22 | Islamabad | Islamabad | Tumair | Tumair | Anwar Kamal | 61101-5576947-5 | 0333-5184411 | Tumair | 33.67559 | 73.28668 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-21 | 12 Ft | 65 Ft | 12-03-21 | 05-04-21 | 640,000/- | 05-05-21 | 640,000/- | Completed | Reverified
14 | 2021-22 | Islamabad | Islamabad | Tumair | Tumair Mohara | Nadeem Abdul Qayoom | 61101-1998445-5 | 0332-5278013 | Tumair Mohra | 33.67597 | 73.28669 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-21 | 12 Ft | 65 Ft | 12-03-22 | 05-04-22 | 640,000/- | 05-05-22 | 640,000/- | Completed | Reverified
15 | 2021-22 | Islamabad | Islamabad | Piaount,Islamabad | Tumari | Taber Hussain | 61101-1807581-3 | 0309-9657479 | Piaount | 33.68 | 73.04 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-2021 | 12 Ft | 65 Ft | 24-11-2021 | 04-01-2022 | 640,000/- | 20-05-2022 | 640,000/- | Completed | ReVerified
16 | 2021-22 | Islamabad | Islamabad | Tumair,Islamabad | Tumair | Waqas Muhmmad Raja | 61101-6144622-7 | 0332-5131623 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-2021 | 12 Ft | 65 Ft | 24-11-2021 | 07-01-2022 | 640,000/- | 20-05-2022 | 640,000/- | Completed | ReVerified
17 | 2021-22 | Islamabad | Islamabad | Mughal | Mughal | Mudasir Iqabal Mirza | 61101-6372843-9 | 0314-5373290 | Mughal | 33,33,17'' | 73,15,11 | 20 Kanal | 20 Kanal | 800,000/- | 08-11-21 | 12 Ft | 65 Ft | 24-11-21 | 05-01-22 | 640,000/- | 20-05-22 | 640,000/- | Complete | Reverified
18 | 2022-23 | Islamabad | Islamabad | Mughal | Mughal | Shamas Zaheer | 61101-4837442-9 | 0314-5373290 | Mughal | 33.5448 | 73.2482 | 20 Kanal | 20 Kanal | 800,000/- | 14-11-22 | 12 Ft | 65 Ft | 12-03-22 | 20-04-23 | 640,000/- | 14-06-23 | 640,000/- | Completed | Reverified
19 | 2022-23 | Islamabad | Islamabad | Kijna,Islamabad | Kijna | Ikram Rasool | 61101-1976372-5 | 0315-7190499 | Kijna | 33.61 | 73.19 | 20 Kanal | 20 Kanal | 800,000/- | 14-11-2022 | 12 Ft | 65 Ft | 23-11-2022 | 03-04-2023 | 640,000/- | 14-06-2023 | 640,000/- | Completed | ReVerified
20 | 2022-23 | Islamabad | Islamabad | Sihala | Sihala | Sibtain Farhat Mirza | 61101-7368980-1 | 0314-5373290 | Sihala | 33.55482 | 73.25313 | 20 Kanal | 20 Kanal | 800,000/- | 14-11-22 | 12 Ft | 65 Ft | 23-11-22 | 04-04-23 | 640,000/- | 04-05-23 | 640,000/- | Completed | Reverified
21 | 2022-23 | Islamabad | Islamabad | Tumair | Tumair | Rehmat Ullah | 61101-6131803-7 | 0316-4895558 | Tumair | 33.67059 | 73.24907 | 20 Kanal | 20 Kanal | 800,000/- | 14-11-22 | 12 Ft | 65 Ft | 23-11-22 | 03-04-23 | 640,000/- | 03-04-23 | 640,000/- | Completed | Reverified
22 | 2022-23 | Islamabad | Islamabad | Tumair | Tumair | Awais Muhammad Raja | 37405-8535825-9 | 0332-5131626 | Tumair | 33,41,20'' | 7317,45'' | 20 Kanal | 20 Kanal | 800,000/- | 14-11-22 | 12 Ft | 65 Ft | 23-11-22 | 31-03-23 | 640,000/- | 20-05-23 | 640,000/- | Complete | Reverified
23 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Imtiaz Ali Khan | 33302-2217525-3 | 3157190499 | Tumair Islamabad | 33.6724 | 73.2428 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
24 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Umair Zafar | 61104-1911395-5 | 3216628036 | Tumair Islamabad | 33.6688 | 73.2952 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
25 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Usman Afzal Ghani | 3463-9561427-9 | 3338112526 | Tumair Islamabad | 33.6749 | 73.2949 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
26 | 2024-2025 | Islamabad | Islamabad | Chirah | - | Akhtar Zaman | 61101-2904602-1 | 3325684141 | Chirah Islamabad | 33.6644 | 73.3117 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
27 | 2024-2025 | Islamabad | Islamabad | Moriyan | - | Kurram Shahzad | 61101-2065319-7 | 3455409449 | Moriyan Islamabad | 33.6687 | 73.2509 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
28 | 2024-2025 | Islamabad | Islamabad | Phulgrahn | - | Raja Ameen Aftab | 61101-3497343-3 | 3005090079 | Phulgrahn Islamabadf | 33.7601 | 73.2428 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
29 | 2024-2025 | Islamabad | Islamabad | Piont | - | Usama Sahbir | 61101-1159793-5 | 3486444951 | Piont Islamabad | 33.7008 | 73.328 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
30 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Jahangir Ahmad | 61101-4803364-3 | 3486444951 | Tumair Islamabad | 33.6775 | 73.2849 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
31 | 2024-2025 | Islamabad | Islamabad | Piont | - | Muhammad Imran | 61101-1083948-1 | 3156219225 | Piont Islamabad | 33.6872 | 73.3162 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
32 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Syed Fazal Hakim | 15601-3241540-3 | 3161511975 | Tumair Islamabad | 33.6774 | 73.2852 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
33 | 2024-2025 | Islamabad | Islamabad | Sihala | - | Sajid Mehmood | 61101-8344775-3 | 3165081844 | Sihala Islamabad | 33.5429 | 73.2195 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
34 | 2024-2025 | Islamabad | Islamabad | Kuri | - | Mateen Murtaza | 33302-7226228-1 | 3215684172 | Kuri Islamabad | 33.6841 | 73.1882 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved
35 | 2024-2025 | Islamabad | Islamabad | Mera Behwal | - | Faizan Murtaza | 61101-6625427-1 | 31453732290 | Mera Behwal Islamabad | 33.7224 | 73.2707 |  |  | 800,000/- | - | 12' | 60' | - | - | - | - | - | Design Vett. | Approved

## solar on DW
Solar Pumping System On Dug Wells
Sr. No. | Fiscal Year | District | Tehsil | Mouza | Union Council | Name of Benificiary | CNIC | Contact No. | Address | GPS Coordinates N E |  | Command Area | Cost Estimate (Rs.) | Issuance of TS Date | Tender Opening Date | Approval for Execution of Scheme Date | Capacity (HP) | Status | Remarks
1 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad ijaz | 61101-7738075-5 | 0318-5335456 | Tumair | 33.688 | 73.2954 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Completed | Reverified
2 | 2020-21 | Islamabad | Islamabad | Saidpur | Araha | Zahid Hussain | 61101-0226457-3 | 0345-5005597 | Araha | 33.6301 | 73.2449 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Completed | Reverified
3 | 2020-21 | Islamabad | Islamabad | Gohkina | Gohkina | Muhammad Saddique | 61101-6131688-5 | 3335289328 | Gohkina | 33.6689 | 73.065 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Completed | Reverified
4 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Azeem Khan | 61101-7554811-7 | 3489513755 | Tumair | 33.628 | 73.2824 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Completed | Reverified
5 | 2020-21 | Islamabad | Islamabad | Mughal | Mughal | Ulfat Hussain Mirza | 61101-1783618-1 | 3135190331 | Mughal | 33.5448 | 73.2482 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Unavailable | Deferred | • System was not available at site.
6 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Muhammad Younas | 37405-5386315-3 | 3015215408 | Tumair | 33.6728 | 73.2824 | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-26 | 2021-05-18 | 2HP | Completed | Reverified | -
7 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Nadeem Ijaz | 61101-7738075-5 | 3185335456 | Tumair , Islamabad | 33,41,17'' | 73,17,43'' | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-27 | 2021-05-19 | 2HP | Completed | Reverified
8 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Malik Zubair Ahmed | 611011767724-5 | 3045359698 | Tumair , Islamabad | 33,41,3'' | 73,18,2'' | 20 Kanal | 426,975/- | 2021-04-14 | 2021-04-28 | 2021-05-20 | 2HP | Completed | Reverified
9 | 2020-21 | Islamabad | Islamabad | Tumair | Tumair | Khalid Saleem | 61101-1981820-5 | 3008544284 | Tumair, Islamabad | 33,41,8'' | 73,18,1'' | 20 Kanal | 426,975/- | 2021-04-15 | 2021-04-29 | 2021-05-21 | 2HP | Completed | Reverified
10 | 2020-21 | Islamabad | Islamabad | Sihala | Sihala | Dr. Hassan Zahoor Abbasi | 37405-2497540-1 | 3228247777 | Sihala , Islamabad | 33,33,26'' | 73,12,54'' | 20 Kanal | 426,975/- | 2021-04-16 | 2021-04-30 | 2021-05-22 | 2HP | Completed | Reverified
11 | 2020-21 | Islamabad | Islamabad | Tarlai Kalan | Tarlai Kalan | Sadia Ghazal | 42201-0309196-4 | 3475355371 | Tarlai Kalan, Islamabad | 33,39,58'' | 73,17,13'' | 20 Kanal | 426,975/- | 2021-04-17 | 2021-05-01 | 2021-05-23 | 2HP | Completed | Deferred | • System was not available at site.
12 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Imtiaz Ali Khan | 33302-2217525-3 | 3157190499 | Tumair Islamabad | 33.6724 | 73.2428 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
13 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Umair Zafar | 61104-1911395-5 | 3216628036 | Tumair Islamabad | 33.6688 | 73.2952 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
14 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Usman Afzal Ghani | 3463-9561427-9 | 3338112526 | Tumair Islamabad | 33.6749 | 73.2949 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
15 | 2024-2025 | Islamabad | Islamabad | Chirah | - | Akhtar Zaman | 61101-2904602-1 | 3325684141 | Chirah Islamabad | 33.6644 | 73.3117 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
16 | 2024-2025 | Islamabad | Islamabad | Moriyan | - | Kurram Shahzad | 61101-2065319-7 | 3455409449 | Moriyan Islamabad | 33.6687 | 73.2509 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
17 | 2024-2025 | Islamabad | Islamabad | Phul Grah | - | Raja Ameen Aftab | 61101-3497343-3 | 3005090079 | Phul Grah Islamabad | 33.7601 | 73.2428 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
18 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Jahangir Ahmad | 61101-4803364-3 | 3486444951 | Tumair Islamabad | 33.7008 | 73.328 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
19 | 2024-2025 | Islamabad | Islamabad | Tumair | - | Syed Fazal Hakim | 15601-3241540-3 | 3161511975 | Tumair Islamabad | 33.6775 | 73.2849 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved
20 | 2024-2025 | Islamabad | Islamabad | Shadra | - | Humayun Ashraf Awan | 61101-9545964-7 | 0300-856211 | Shadra Islamabad | 33.6211 | 73.2824 | 20 Kanal | 500000 | - | - | - | 2HP | Design Vett. | Approved